Plan G3.C1.P6 Hoosier Training Association "Learn to Earn" (Project LTE). Plan Source:; 2001 Annual Report. Goal 3:; Economic Opportunity. Category 1:; Workforce Development. Plan 6:; Hoosier Training Association "Learn to Earn" (Project LTE).

|  | I. Baseline. Program/Project Description:; Industry-based training programs are needed in order to train EZ residents with skill sets required by area industries.. Baseline:; There are a limited number of job skills training programs currently in existence for Zone residents to prepare them for careers within the healthcare industry and become self sufficient.. Proposed Outcome:; Provide Zone residents with job training and employment opportunities within the healthcare industry.. HHS EZ Funds(Round I):; $0.00. HUD EZ Funds(Round II):; $50,000.00. Amount of HUD Round II EZ grant under contract/agreement with third party: $0.00. Non-EZ/EC Grant Funds:; $53,400.00. Total Budget:; $103,400.00. Plan Status:; Active. Review Status:; Approved. |  |
| --- | --- | --- |

|  | II. Sources of Program Funds. A.; HHS EZ Funds (Round I):; $0.00. B.; HUD EZ Funds (Round II):; $50,000.00. Amount of HUD Round II EZ grant under contract/agreement with third party:; $0.00. C.; Non-EZ/EC Grant Funds:; $53,400.00. Participating Entity (Non EZ/EC Grant Funds); Private; Cash; In-Kind. 1.; CDBG; No; $53,400.00; $0.00. Total; $53,400.00; $0.00. |  |
| --- | --- | --- |

|  | III. Uses of Program Funds. Lead Implementing Entity; Amount. A.; Hoosier Training Program; $103,400.00. Total; $103,400.00. |  |
| --- | --- | --- |

|  | IV. Status of Projected Milestones. P r o j e c t e d; % Complete as of. Milestones; Start; End; 07/01/2000; 06/30/2001. A.; Recruit EZ residents; 01/04/1999; 10/31/2001; 100; 100. B.; Identify and hire instructors; 01/04/1999; 12/29/2001; 100; 100. C.; Start home healthcare training program; 02/01/1999; 10/31/2001; 100; 100. D.; Develop partnerships with healthcare employers for on-the-job training (practicums) and employment of graduating trainees.; 02/01/1999; 10/31/2001; 50; 75. E.; Coordinate hiring activities with partnering employers for graduating trainees.; 05/10/1999; 10/31/2001; 50; 75. F.; Conduct post-employment case management for EZ residents securing full-time employment.; 05/10/1999; 12/31/2002; 50; 50. |  |
| --- | --- | --- |

|  | V. Progress Towards Projected Outputs. Outputs; Projected; To Date. A.; Job Training. 1.; Number of job training programs; 1; 1. 2.; Number of EZ/EC residents trained; 90; 32. 3.; Number of EZ/EC resident trainees placed in jobs; 65; 24. B.; Job Match. C.; Job Fairs. D.; Other Workforce Development Programs. E.; Other unique output measurement:. 1.; Maintain 70% employment retention rate of employed Hoosier graduates.; 45; 23. Percentage of outputs benefiting EZ/EC Residents; 100%; 100%. |  |
| --- | --- | --- |