# Appendix H. Assessment and Evaluation Plan Timeline

The following table presents the tentative timeline for this assessment/evaluation project. Dates are subject OMH review and approval.

| ### SRA International, Inc. National CLAS Standards Assessment and Evaluation Timeline |  |
| --- | --- |
| (Approximate) Date | Actions |
| 9/22/2014 | Submit OMB package to HHS OMH for submission |
| Pending HHS OMH | HHS OMH submits OMB package |
| Phase 1 |  |
| 10/20/2014-11/3/2014 | Develop list of key CLAS and National CLAS Standards stakeholders for interview |
| 11/3/2014 | Submit health and health care organization pre-screening questionnaire to identify “CLAS Adopter” population to HHS OMH for review and approval |
| 11/3/2014-11/17/2014 | Submit to and discuss with HHS OMH the list of CLAS and National CLAS Standards stakeholders and health/health care organization association list for interviews and surveys |
| 11/17/2014 | Receive feedback from HHS OMH on health and health care organization pre-screening questionnaire to identify “CLAS Adopter” population |
| 11/24/2014-12/31/2014* | Upon approval of HHS OMH begin contacting key CLAS and National CLAS Standards stakeholders to schedule interview and solicit health and health care organization nominations |
| 11/24/2014-1/16/2015* | Upon approval of HHS OMH disseminate health and health care organization pre-screening questionnaire to identify “CLAS Adopter” population |
| 12/2014 | Begin developing peer-review publication of CLAS and National CLAS Standards literature review with HHS OMH |
| 2/2015 | Submit peer-review publication |
| 1/5/2015-2/27/2015* | Conduct stakeholder interviews |
| 2/2/2015-3/13/2015 | Begin contacting and engaging key informants in health and health care organizations |
| 3/2/2015-3/27/2015 | Analyze and summarize data from stakeholder interviews |
| Phase 2 |  |
| 4/6/2015-5/29/2015 | Conduct health and health care organization interviews and site visits |
| 4/6/2015-5/29/2015 | Administer OMB-approved survey via online to health and health care organization leadership and staff |
| 4/13/2015 | Submit and review data analyses from Stakeholder interviews with HHS OMH |
| 5/2015 | Discuss plan for peer-review publications with HHS OMH |
| 5/4/2015 | Receive feedback and approval on data analyses from Stakeholder interviews from HHS OMH |
| 5/11/2015-5/29/2015 | Upon HHS OMH approval, share summary of data analyses with key CLAS and National CLAS Standards stakeholders |
| 6/2015 | Develop manuscripts for peer-review submission in partnership with HHS OMH staff |
| 6/1/2015-7/17/2015 | Analyze and summarize health and health care organization data |
| 7/20/2015-7/31/2015 | Synthesize data to develop preliminary implementation model for the National CLAS Standards |
| 8/2015 | Submit peer-review publication |
| 8/3/2015 | Submit health and health care organization data analyses and preliminary model to HHS OMH for review and feedback |
| 8/21/2015 | Receive feedback on data health and health care organization data analyses |
| 8/24/2015-8/31/2015 | Upon HHS OMH approval, share initial implementation model with HHS OMH and key CLAS and National CLAS Standards stakeholders |
| 8/24/2015-8/31/2015 | Continue developing draft Assessment and Evaluation Report Summary, policy brief(s), and technical assistance materials based on implementation model |
| 8/31/2015 | Submit draft of Assessment and evaluation Report Summary, draft policy brief(s), and technical assistance materials to HHS OMH for review |
| 9/22/2015 | Receive feedback from HHS OMH on submitted drafts materials |
| 9/30/2015 | Submit Final Assessment and Evaluation Report Summary to HHS OMH |
| 9/30/2015 | Upon HHS OMH approval, disseminate policy brief(s) and technical assistance materials publicly |