The following table presents the tentative timeline for this evaluation project.

HHS OMH and the SRA-HDDP Evaluation Team will need at least 10 business days for review and provision of feedback/revision. Lengthier reports and deliverables will require 15 days for review and provision of feedback/revision. Final approval from HHS OMH will be sought for all data collection efforts, survey/questionnaires/study protocol development, reports, presentations, and publications before public release or dissemination.

| ### SRA International, Inc. National CLAS Standards Evaluation Timeline |  |
| --- | --- |
| (Approximate) Date | Actions |
| 1/17/2014 | Evaluation plan submitted to Project Officer and Project Director |
| 3/3/2014 | Received evaluation plan feedback and revise |
| 3/17/2014 | Finalize subcontract with George Mason |
| 4/25/2014 | Final evaluation plan approved by HHS OMH |
| 4/28/2014-5/24/2014 | Draft survey and interview protocols |
| 4/28/2014-8/31/2014 | Conduct literature review on CLAS and the National CLAS Standards |
| 6/4/2014 | Submitted interview protocols to HHS OMH for review |
| 6/30/2014 | Evaluation project materials submitted to George Mason Institutional Review Board (IRB) for review and approval. |
| 7/2/2014 | Submit draft interview protocols and survey and to Advisory Group for review and feedback (upon OMH review and approval) |
| 7/21/2014 | Received feedback on survey and interview protocols from Advisory Group |
| 7/21-7/22/2014 | Revised interview protocols and survey |
| 7/23/2014-8/8/2014 | Pilot test interview protocols and survey |
| 8/8/2014-8/22/2014 | Analyze pilot test data and summarize results; Revise interview protocols and surveys based on pilot test data |
| 8/29/2014 | Submit revised interview protocols and survey to HHS OMH for review and approval |
| 9/15/2014-9/19/2014 | Revise interview protocols and survey per HHS OMH feedback |
| 9/2/2014 | Submit OMB package to HHS OMH for review |
| 9/18/14 | Receive feedback from HHS OMH on OMB package |
| 9/29/14 | Submit revised OMB package to HHS OMH for submission |
| 9/29/14 | Submit draft of CLAS and National CLAS Standards literature review to HHS OMH for review |
| 12/1/2014 | Submit revised CLAS and National CLAS Standards literature review to HHS OMH for review and approval |
| 1/2015 | Conduct Phase 1 publication review meeting with OMH |
| Phase 1 |  |
| 10/20/2014-11/3/2014 | Develop list of key CLAS and National CLAS Standards stakeholders for interview |
| 11/24/14 | Submit the list of CLAS and National CLAS Standards stakeholders and health/health care organization association list for interviews and surveys to HHS OMH for review and approval |
| 11/24/2014 | Submit health and health care organization pre-screening questionnaire to identify “CLAS Adopter” population HHS OMH for final review and approval |
| 12/2014 | Discuss with HHS OMH the list of CLAS and National CLAS Standards stakeholders and health/health care organization association list for interviews and surveys |
| 12/31/2014 | Submit revised list of CLAS and National CLAS Standards Stakeholders and health/health care organization association list for interviews and surveys for HHS OMH final review and approval |
| 2/2/15 - 3/23/15* | Upon approval of HHS OMH begin contacting key CLAS and National CLAS Standards stakeholders to schedule interview and solicit health and health care organization nominations |
| 2/2/15 - 3/23/15* | Upon approval of HHS OMH, disseminate health and health care organization pre-screening questionnaire to identify “CLAS Adopter” population |
| 2/23/15 – 4/17/15* | Conduct stakeholder interviews |
| 3/23/15 – 5/1/15* | Begin contacting and engaging key informants in health and health care organizations |
| 3/30/15* | Submit draft data analysis plan for stakeholder interviews to HHS OMH for review and approval |
| 4/27/15* | Submit publication plan for Phase 2 of the project for OMH review |
| 4/20/15 – 5/15/15* | Analyze and summarize data from stakeholder interviews |
| 6/2015* | Submit revised publication plan for Phase 2 of the project OMH review and approval. |
| 7/2015* | Conduct Phase 2 publication review meeting with OMH |
| Phase 2 |  |
| 5/25/15 – 7/17/15* | Conduct health and health care organization interviews and site visits |
| 5/25/15 – 7/17/15* | Administer OMB-approved survey via online to health and health care organization leadership and staff |
| 6/8/15* | Submit data analyses from Stakeholder interviews to HHS OMH for review |
| 6/2015* | Review data analyses from Stakeholder interviews with HHS OMH |
| 6/26/15* | Submit data analysis plan for health care organization and site visits and web survey for OMH review and approval |
| 7/6/15 – 7/24/15* | Upon HHS OMH approval, share summary of data analyses with key CLAS and National CLAS Standards stakeholders |
| 7/27/15 – 9/11/15* | Analyze and summarize health and health care organization data |
| 9/28/15* | Submit health and health care organization data analyses to HHS OMH for review |
| 10/26/15* | Submit draft of Evaluation Report for HHS OMH review |
| 11/2/15* | Submit revised draft of health and health care organization data analyses to HHS OMH for final review and approval |
| 11/16/15 – 11/25/15* | Upon HHS OMH approval, share evaluation results with key CLAS and National CLAS Standards stakeholders |
| 12/24/15* | Submit revised final Evaluation Report to HHS OMH for review and approval |

*Contingent upon receipt of OMB and GMU IRB approval