## Providing Primary Care and Preventive Medical Services

in Ryan White-funded Medical Care Settings

Study Timeline

| Activity | Date(s) |
| --- | --- |
| - OMB Approval | September 2015 |
| - Surveys completed by 130 Clinic Director Survey | October 2015 |
| 2b. Analysis of Clinic Director Survey Sampling of Agencies who responded to the survey | November 2015 |
| - Surveys completed by Clinicians (3 clinicians from 30 clinics) | December 1, 2015 - January 15, 2016 |
| 3b. Analysis of Clinician Survey | January 16-30, 2016 |
| - Data Extraction competed by 30 clinics | December 1, 2015 - January 15, 2016 |
| 4b. Analysis of Data Extraction | January 16-30, 2016 |
| - Interviews with medical directors | February 2016 |
| 5b. Analysis of Medical Director Interviews | March 1-15, 2016 |
| - Additional analysis and draft report | March 15 - May 15, 2016 |
| - Conduct a presentation of project findings to HRSA staff. | May 26, 2016 |
| - Submit final study report to HAB. | June 23, 2016 |