NATIONAL DROUGHT RESPONSE PLAN TASK TRACKER – 7/12/2016

|  |  | Lead Coordinating Agency(ies) | Action Leader(s) | Email Address |
| --- | --- | --- | --- | --- |
| Goal 3: Drought Planning and Capacity Building | Goal Leader: NOAA- Claudia Nierenberg |  |  | claudia.nierenberg@noaa.gov |
| 4. Support State, Tribal, Local and Territorial Health Departments |  | HHS-CDC | HHS-CDC- Amy Wolkin | AJF9@cdc.gov |
| Develop a guide about the state of drought-related public health activities, including resources to help states prepare for and respond to drought (By March 1, 2018) |  |  |  |  |
| Literature review to determine most recent scientific knowledge and activities (By December 31, 2016) |  |  |  |  |
| Report describing semi-structured in-depth interviews (June 1, 2017) |  |  |  |  |
| Report describing assessment of state drought plans (June 30, 2017) |  |  |  |  |
| Outline of guide (September 1, 2017) |  |  |  |  |
| Conduct 2 CASPERs in drought-affected states, complete report summarizing drought-related CASPERs (August 1, 2017) |  |  |  |  |
| Select states for CASPER (July 31, 2016) |  |  |  |  |
| Conduct 1st CASPER (October 31, 2016) |  |  |  |  |
| Conduct 2nd CASPER (June 30, 2017) |  |  |  |  |
| Write Report (August 1, 2017) |  |  |  |  |