## Sheet1
APPENDIX H 1- Feedback Submitted by USDA Professional Standards Training Tracker Tool Testing/Working Group Part 1
Number | User Role | Name of Test Case | Step # in the test case | Tested By | Stakeholder Comments | FNS/Contractor Notes
1 | Manager | Enter & Edit Training | 18 | Marlene Stein | When Entering training for manager and employee did not load | confirm that the profiles were set up under same school and district.
2 | Manager | Create employee profile | 28 | Marlene Stein | Verify that the First and last name fields are not editable | name should not be editable since coming via eauth- ensure this
3 | Employee | Create and edit profile | 11 | Phyllis Hodges | School name was not in the data base. I have gone in and out of this field a few times so now I think I have it in there four times! | disscuss opions on how user can seamlessly add new chool information if not available on the tool and be able to create the profile to log in
4 | Employee | Create and edit profile | 12 | Phyllis Hodges | Since it was not in the data base, it did not pre-populate so I was not sure if this was a pass or fail. | clarify what the issue is
5 | Employee | Create and edit profile | 20 | Phyllis Hodges | Had to close the window manually. | check on the bug
6 | Employee | Create and edit profile | 32 | Phyllis Hodges | The message appears. Not sure about the accuracy since it says 0 days and 0.00 hours. Will look at again later. | 0 days - opening dashboard page - check on the number of days
7 | Employee | Enter & Edit Training | 17 | Phyllis Hodges | This field selects the learning objective - but it does not react the same way as other fields. You do not see the selected topic populate as you would expect. | discuss some options make selection easier and more seamless
8 | Manager | NA | NA | Marlene Stein | Be able to view the title of an employees training similar to view employees page | New requirement to add additional view for the Manager and Employee to view training
9 | Manager | Create profile page | 15 | Mimi Trinh | School_Type | Change to School Type
10 | Employee | Create profile page | 26, 27 and 43 | Kim Goebels | Unable to input managers email address | discuss making this not a required field
11 | Employee | Create profile page | 24,27,34,38,45 | Dawn Soto | Unable to input managers email address | discuss making this not a required field