| Schedule (in weeks): BRFSS Cognitive Testing Questions 2023 |  |  | N=25 completes |
| --- | --- | --- | --- |
|  | Begin Date | End Date |  |
| Begin recruitment | Week 1 | ongoing |  |
| Conduct Interviews | Week 2 | Week 4 |  |
| Enter Notes | Week 2 | Week 5 |  |
| Conduct analysis | Week 6 | Week 10 |  |
| Prepare 1st draft of report / submit to CDC | Week 8 | Week 10 |  |
| Receive CDC feedback on draft report | Week 11 | Week 11 |  |
| Revise and submit final report to CDC | Week 13 | Week 13 |  |