## CY 1-2 (hidden)
Implementation Schedule | [9 empty] | U.S. Department of Housing | [17 empty] | OMB Approval No. 2577-0191
Indian Community Development Block Grant (ICDBG) | [9 empty] | and Urban Development | [17 empty] | (exp. 9/30/2021)
Office of Public and Indian Housing
See Instructions and Public Reporting Statement on back.
Submit a separate implementation schedule for each project category.
1. Name of Applicant (as shown in item 5. Standard Form 424) | [7 empty] | 2. Application/Grant Number | [7 empty] | 3. | x | Original (First Submission to HUD) | [9 empty] | Date (mm/dd/yy)
My Tribe of Oklahoma | [7 empty] | (to be assigned by HUD) | [9 empty] | Pre-Award Submission | [9 empty] | 2024-04-08
[8 empty] | OKC-12345 | [9 empty] | Amendment (submitted after grant)
4. Name of Project (as shown on form HUD-4123) |  |  |  |  | 5. Period of Performance | [7 empty] | Expected Close Out Date
Purchase or Construct New Rental Units |  |  |  |  | Start Date (mm/dd/yy) |  |  |  | End Date (mm/dd/yy) |  |  |  | (mm/dd/yy)
[5 empty] | 2025-03-01 |  |  |  | 2027-03-01 |  |  |  | 2027-05-01
6. Environmental Review Status
| Exempt (as described in 24 CFR 58.34) |  | Under Review (review underway; | [5 empty] | Finding of No Significant Impact (Finding made that request for release of | [15 empty] | Categorically Excluded
|  |  | findings not yet made) | [5 empty] | funds for project is not an action which may significantly affect the environment) | [15 empty] | (as described in 24 CFR 58.35)
| EIS Required (Finding that project may | x | Not Started | [5 empty] | Certification (Environmental review completed; | [14 empty] | 7. Tribal Fiscal Year (mm/dd/yy)
| significantly affect environment or |  | (Review not yet begun) | [5 empty] | certification and request for release of funds | [14 empty] | 2025-09-30
| EIS automatically required by 24 CFR 58.37) | [7 empty] | being prepared for submission.)
8. Task List |  |  |  | 9. Schedule (use Calendar Year (CY) quarters. Fill-in the CY below. See detailed instructions on back.)
(List tasks such as environmental assessment, acquisition, etc.) |  |  |  | Calendar Year | [5 empty] | 2025 | [5 empty] | Calendar Year | [5 empty] | 2026 | [5 empty] | Date (mm/dd/yy)
|  |  |  | 1st Qtr. |  |  | 2nd Qtr. |  |  | 3rd Qtr. |  |  | 4th Qtr. |  |  | 5th Qtr. |  |  | 6th Qtr. |  |  | 7th Qtr. |  |  | 8th Qtr. |  |  | (if exceeds 8th qtr.)
(Insert lines as needed. Left click, insert, entire row) |  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
HUD Notice of Award Letter | bar: 1st Qtr. M
Prepare Environmental | bar: 1st Qtr. M to 3rd Qtr. A
Advertise RFQ | bar: 3rd Qtr. A to 3rd Qtr. S
Preliminary Design | bar: 4th Qtr. O to 6th Qtr. M
Negotiate Price | bar: 6th Qtr. J to 7th Qtr. S
Select Contractor | bar: 8th Qtr. O to 8th Qtr. D
10. Planned Drawdowns by Quarter | [27 empty] | TOTAL
(enter amounts non-cumulatively) |  |  |  | 1st Qtr. J: 129375; 2nd Qtr. A: 258750; 3rd Qtr. J: 258750; 4th Qtr. O: 258750; 5th Qtr. J: 129375; 6th Qtr. A: 125000; 7th Qtr. J: 125000; 8th Qtr. O: 125000 | 1410000
11. Cumulative Drawdown | [27 empty] | TOTAL
(if more than one page, enter total on last page) |  |  |  | 1st Qtr. J: 129375; 2nd Qtr. A: 388125; 3rd Qtr. J: 646875; 4th Qtr. O: 905625; 5th Qtr. J: 1035000; 6th Qtr. A: 1160000; 7th Qtr. J: 1285000; 8th Qtr. O: 1410000 | 1410000

## CY 3-4 (hidden)
Implementation Schedule | [8 empty] | U.S. Department of Housing | [17 empty] | OMB Approval No. 2577-0191
Indian Community Development Block Grant (ICDBG) | [8 empty] | and Urban Development | [17 empty] | (exp. 9/30/2021)
Office of Public and Indian Housing
See Instructions and Public Reporting Statement on back.
Submit a separate implementation schedule for each project category.
1. Name of Applicant (as shown in item 5. Standard Form 424) | [6 empty] | 2. Application/Grant Number | [7 empty] | 3. |  | Original (First Submission to HUD) | [9 empty] | Date (mm/dd/yy)
[7 empty] | (to be assigned by HUD) | [9 empty] | Pre-Award Submission
Amendment (submitted after grant)
4. Name of Project (as shown on form HUD-4123) |  |  |  | 5. Period of Performance | [7 empty] | Expected Close Out Date
Purchase or Construct New Rental Units |  |  |  | Start Date (mm/dd/yy) |  |  |  | End Date (mm/dd/yy) |  |  |  | (mm/dd/yy)
6. Environmental Review Status
| Exempt (as described in 24 CFR 58.34) | Under Review (review underway; | [5 empty] | Finding of No Significant Impact (Finding made that request for release of | [15 empty] | Categorically Excluded
|  | findings not yet made) | [5 empty] | funds for project is not an action which may significantly affect the environment) | [15 empty] | (as described in 24 CFR 58.35)
| EIS Required (Finding that project may | Not Started | [5 empty] | Certification (Environmental review completed; | [14 empty] | 7. Tribal Fiscal Year (mm/dd/yy)
| significantly affect environment or | (Review not yet begun) | [5 empty] | certification and request for release of funds
| EIS automatically required by 24 CFR 58.37) | [6 empty] | being prepared for submission.)
8. Task List |  |  | 9. Schedule (use Calendar Year (CY) quarters. Fill-in the CY below. See detailed instructions on back.)
(List tasks such as environmental assessment, acquisition, etc.) |  |  | Calendar Year | [5 empty] | 2027 | [5 empty] | Calendar Year | [5 empty] | 2028 | [5 empty] | Date (mm/dd/yy)
|  |  | 1st Qtr. |  |  | 2nd Qtr. |  |  | 3rd Qtr. |  |  | 4th Qtr. |  |  | 5th Qtr. |  |  | 6th Qtr. |  |  | 7th Qtr. |  |  | 8th Qtr. |  |  | (if exceeds 8th qtr.)
(Insert lines as needed. Left click, insert, entire row) |  |  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Design 65% | bar: 1st Qtr. J to 2nd Qtr. A
Final Design | bar: 2nd Qtr. M to 4th Qtr. O
Construction | bar: 4th Qtr. N to 8th Qtr. D
10. Planned Drawdowns by Quarter | [26 empty] | TOTAL
(enter amounts non-cumulatively) |  |  | 1st Qtr. J: 80000; 2nd Qtr. A: 145000; 3rd Qtr. J: 80000; 4th Qtr. O: 90000; 5th Qtr. J: 500000; 6th Qtr. A: 450000; 7th Qtr. J: 295000; 8th Qtr. O: 175000 | 1815000
11. Cumulative Drawdown
(if more than one page, enter total on last page) |  |  | 1st Qtr. J: 1490000; 2nd Qtr. A: 1635000; 3rd Qtr. J: 1715000; 4th Qtr. O: 1805000; 5th Qtr. J: 2305000; 6th Qtr. A: 2755000; 7th Qtr. J: 3050000; 8th Qtr. O: 3225000 | 3225000

## CY 5 (hidden)
Implementation Schedule | [8 empty] | U.S. Department of Housing | [9 empty] | OMB Approval No. 2577-0191
Indian Community Development Block Grant (ICDBG) | [8 empty] | and Urban Development | [9 empty] | (exp. 9/30/2021)
Office of Public and Indian Housing
See Instructions and Public Reporting Statement on back.
Submit a separate implementation schedule for each project category.
1. Name of Applicant (as shown in item 5. Standard Form 424) | [6 empty] | 2. Application/Grant Number | [7 empty] | 3. | Original (First Submission to HUD) |  |  | Date (mm/dd/yy)
My Tribe of Oklahoma | [6 empty] | (to be assigned by HUD) | [8 empty] | Pre-Award Submission
[7 empty] | OKC-12345 | [8 empty] | Amendment (submitted after grant)
4. Name of Project (as shown on form HUD-4123) |  |  |  | 5. Period of Performance | [7 empty] | Expected Close Out Date
Purchase or Construct New Rental Units |  |  |  | Start Date (mm/dd/yy) |  |  |  | End Date (mm/dd/yy) |  |  |  | (mm/dd/yy)
6. Environmental Review Status
| Exempt (as described in 24 CFR 58.34) | Under Review (review underway; | [5 empty] | Finding of No Significant Impact (Finding made that request for release of | [9 empty] | Categorically Excluded
|  | findings not yet made) | [5 empty] | funds for project is not an action which may significantly affect the environment) | [9 empty] | (as described in 24 CFR 58.35)
| EIS Required (Finding that project may | Not Started | [5 empty] | Certification (Environmental review completed; | [8 empty] | 7. Tribal Fiscal Year (mm/dd/yy)
| significantly affect environment or | (Review not yet begun) | [5 empty] | certification and request for release of funds
| EIS automatically required by 24 CFR 58.37) | [6 empty] | being prepared for submission.)
8. Task List |  |  | 9. Schedule (use Calendar Year (CY) quarters. Fill-in the CY below. See detailed instructions on back.)
(List tasks such as environmental assessment, acquisition, etc.) |  |  | Calendar Year | [5 empty] | 2029 | [9 empty] | Date (mm/dd/yy)
|  |  | 1st Qtr. |  |  | 2nd Qtr. |  |  | 3rd Qtr. |  |  | 4th Qtr. | [6 empty] | (if exceeds 8th qtr.)
(Insert lines as needed. Left click, insert, entire row) |  |  | J | F | M | A | M | J | J | A | S | O | N | D
Substantial Completion | bar: 1st Qtr. J to 1st Qtr. M
Clear Punch List | bar: 2nd Qtr. A to 2nd Qtr. J
Project Close-out | bar: 3rd Qtr. J to 3rd Qtr. S
10. Planned Drawdowns by Quarter | [18 empty] | TOTAL
(enter amounts non-cumulatively) |  |  | 1st Qtr. J: 80000; 2nd Qtr. A: 145000; 3rd Qtr. J: 80000 |  |  |  |  | 305000
11. Cumulative Drawdown
(if more than one page, enter total on last page) |  |  | 1st Qtr. J: 3305000; 2nd Qtr. A: 3450000; 3rd Qtr. J: 3530000 |  |  |  |  | 3530000

## Instructions
Instructions for Completing 4123 and 4125
FORM 4123
Section
1 | Input Applicant name.
2 | Insert the grant number if it has been assigned by HUD. Use the grant number(s) applicable to the program(s) you are reporting on (ICDBG or IHBG Competitive, or both). Leave blank if unknown at time of application.
3 | Check the appropriate box associated with the form submission. Enter the date you completed this form.
4 | Enter the project name. On the rows below, enter project costs. Use columns (b), (c) and (d) to indicate the applicable source for each line item. Use column (f) to describe the source of funds in column (d).
5 | Enter planned administrative expenses, including (if applicable) indirect costs and audit costs. Administrative costs must not exceed 20% of the grant.
6 | Enter amount of ICDBG funds requested for technical assistance, if applicable. No more than 10% of ICDBG funds requested may be used for technical assistance. If funds are requested under this line item, a separate project description must accompany the application to describe the technical assistance the application intends to obtain. Only technical assistance costs associated with the development of a capacity to undertake a specific funded program activity are eligible (24 CFR 1003.206).
7 | Enter amount of ICDBG funds requested for Public Services. Public Service costs must not exceed 15% of the total ICDBG grant.
FORM 4125
Section
1 | Applicant Name: Auto populates from Form 4123.
2 | Insert the grant number if it has been assigned by HUD. Use the grant number(s) applicable to the program(s) you are reporting on (ICDBG or IHBG Competitive, or both). Leave blank if unknown at time of application.
3 | Input an "X" in the appropriate box associated with the form submission.
4 | Enter the date you completed this form.
5 | Project Name: Auto populates from Form 4123.
6 | Period of Performance: Insert Start Date and End Date.
7 | Expected Close Out Date: auto-populates 90 days from period of performance end date in from Box 6.
8 | Insert an "X" in the box that best describes current Environmental Review status.
9 | Insert description of task.
10 | Insert anticipated start and end month/year of task.

## Form 4123
Cost Summary |  |  |  |  | U.S. Department of Housing |  |  |  | OMB Approval No.0000-0000
Indian Community Development Block |  |  |  |  | and Urban Development |  |  |  | (exp. 00/00/0000)
Grant (ICDBG) and Indian Housing Block |  |  |  |  | Office of Public and Indian Housing
Grant Competitive (IHBG)
See Instructions and Public Reporting Statement
1. Name of Applicant (as shown on Standard Form 424) | [6 empty] | 2. Grant Number (assigned by HUD)
3 |  | Original (Check here if this | Amendment | [5 empty] | Date (mm/dd/yyyy)
|  | is the first submission to HUD) | (Check here if submitted after initial application)
4. | Project Name & Category (see instructions tab) (a) |  |  | Planned ICDBG Expenditures (b) | Planned IHBG Competitive Funds Expenditures (c) | Planned Other Federal and Non-Federal Funds Expenditures (d) |  | Total Planned Expenditures (e) | Source of Other Funds (Column d) for each Activity (f)
Project Name:
0
0
0
0
0
0
0
0
0
0
0
5. | Administration
| a | Planning and Administration Cost | [5 empty] | 0
| b | Indirect Costs: Enter indirect costs to be charged to the Program pursuant to a cost allocation plan. | [5 empty] | 0
| c | Audit: Enter estimated cost of Program share of financial audits. | [5 empty] | 0
| Administrative Total |  |  | 0 | 0 | 0 |  | 0
6. | Technical Assistance Enter amount requested for technical assistance. (up to 10% of total ICDBG Grant) | [6 empty] | 0
7. | Public Service Component: up to 15% of ICDBG grant. | [6 empty] | 0
8. | TOTAL EXPENDITURES |  |  | 0 | 0 | 0 |  | 0
Public reporting burden for this collection of information is estimated to average 40 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. This agency may not collect this information, and you are not required to complete this form, unless it displays a currently valid OMB control number. This collection of information requires that each eligible applicant submit information to enable HUD to select the best projects for funding during annual competitions for these Grant Programs. The information will be used by HUD to determine whether applications meet minimum screening eligibility requirements and application submission requirements. Applicants provide general information about the project which is preliminary to the review of the applicant’s response to the criteria for rating the application. The information is essential for HUD in monitoring grants to ensure that grantees are making proper use of Federal dollars. Responses to the collection are required by Section 105 of the Department of Housing and Urban Development Reform Act (P.L. 101-235) as amended by the Cranston-Gonzales National Affordable Housing Act of l990. The information requested does not lend itself to confidentiality.

## Form 4125
Implementation Schedule |  |  |  | U.S. Department of Housing | [6 empty] | OMB Approval No.0000-0000
Indian Community Development Block Grant (ICDBG) |  |  |  | and Urban Development | [6 empty] | (exp. 00/00/0000)
and Indian Housing Block Grant Competitive (IHBG) |  |  |  | Office of Public and Indian Housing
See Instruction Tab and Public Reporting Statement.
Submit a separate implementation schedule for each project category.
1. Name of Applicant (as shown on Standard Form 424) |  |  |  | 2. Grant Number (assigned by HUD) |  |  | 3. |  | Original (First Submission to HUD) |  | 4. Date (mm/dd/yy)
Auto Populates from Form 4123 | [8 empty] | Amendment (submitted after initial application)
5. Name of Project (as shown on form HUD-4123) |  |  | 6. Period of Performance |  |  | 7. Expected Close Out
Auto Populates from Form 4123 |  |  | Start Date (mm/dd/yy) |  | End Date (mm/dd/yy) | Date (mm/dd/yy)
auto populates
8. Environmental Review Status
| Exempt (as described in 24 CFR 58.34) | Under Review (review underway; |  |  | Finding of No Significant Impact (Finding made that request for release of |  |  |  |  | Categorically Excluded
|  | findings not yet made) |  |  | funds for project is not an action which may significantly affect the environment) |  |  |  |  | (as described in 24 CFR 58.35)
| EIS Required (Finding that project may | Not Started |  |  | Certification (Environmental review completed;
| significantly affect environment or | (Review not yet begun) |  |  | certification and request for release of funds
| EIS automatically required by 24 CFR 58.37) |  |  |  | being prepared for submission.)
9. Task List (List tasks such as environmental assessment, acquisition, etc.) | [7 empty] | 10. Schedule (anticipated start and end date of task) mm/yy
(Insert lines as needed. Home tab, cells, insert sheet row) | [9 empty] | Start Date | End Date
Public reporting burden for this collection of information is estimated to average 40 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestion for reducing this burden, to the Reports Management Officer, Paperwork Reduction Project (2577-0191), Office of Information Technology, U.S. Department of Housing and Urban Development, Washington D.C. 20410-3600. This agency may not collect this information, and you are not required to complete this form, unless it displays a currently valid OMB control number. This collection of information requires that each eligible applicant submit information to enable HUD to select the best projects for funding during annual competitions for these Grant Programs. The information will be used by HUD to determine whether applications meet minimum screening eligibility requirements and application submission requirements. Applicants provide general information about the project which is preliminary to the review of the applicant’s response to the criteria for rating the application. The information is essential for HUD in monitoring grants to ensure that grantees are making proper use of Federal dollars. Responses to the collection are required by Section 105 of the Department of Housing and Urban Development Reform Act ( P . L . 101-235) as amended by the Cranston-Gonzales National Affordable Housing Act of l990. The information requested does not lend itself to confidentiality.